## Slide 1: ESCO Mapping Pilot
Part II :: Planning
Agis Papantoniou, Senior Project Manager, TenForce
Johan De Smedt, CTO, TenForce
Karel Kremer, Software and Knowledge Engineer, TenForce

## Slide 2: Objectives
Identify tasks and actions
Agree on schedule (including workshops)
Present deliverables

## Slide 3: Overview

## Slide 4: Step 1 - Convert National Classifications

## Slide 5: Step 2 - Prepare Case Studies

## Slide 6: Step 3 - Contextualize Case Studies

## Slide 7: Step 4 - Assessing Interoperability

## Slide 8: Step 5 - Document the results

## Slide 9: Tasks and Actions
Responsible | Action | Date
PES | Provide national classification | 23/07/2014
TenForce/SEC | Transform classification and load for alignment | 31/07/2014
TenForce/SEC | Automatic alignment and manual correction | 14/08/2014
PES | Provide use cases (JV – CV) with hidden match scores | 26/08/2014
PES | Provide Statistics on chosen sectors | 26/08/2014
TenForce/SEC | Develop 2x3 cases JV – CV matching | 18/08/2014
TenForce/SEC | Define evaluation grid for alignment | 28/08/2014
PES (/w TF support) | Code documents with PES structure and provide feedback | 30/09/2014
TenForce/SEC | Map coded documents to ESCO | 02/10/2014
TenForce/SEC (/w PES support) | Evaluate (information loss, consistency, matching) | 23/10/2014
TenForce/SEC | Final Report | 14/11/2014
(Dates are indicative)

## Slide 10: Main Deliverables
DLV | Description
DLV01 | Translation tables (partial mappings)
DLV02 | Assessment criteria (grid)
DLV03 | 6 case studies, each in English, French, Dutch, Czech and Spanish
DLV04 | New structured docs
DLV05 | Interoperability assessment report
DLV06 | Final report
DLV07 | Report describing support to PESs
All workshops will be supported by minutes and reports
TenForce and the ESCO SEC will support the PES throughout the whole project

## Slide 11: Workshops
(Dates are indicative)
Workshop | Date
WS1 – Kick off workshop | 17/07/2014
WS2 – Transforming JV/CV documents to NOC | 14/08/2014
WS3 – Support transcoding | 02/10/2014
WS4 – Report on interoperability | 23/10/2014
WS5 – Final workshop | 21/11/2014

## Slide 12: Questions?
Thank you for your attention